## JOB TYPE
JOBTYPEID | JOB TYPE DESCRIPTION
1 | CONSTRUCTION ONLY
2 | DEVELOPMENT TO CONSTRUCTION
3 | MANUFACTURING
4 | PROCUREMENT

## STAGE
Stage
1 | Strategy & Feasibility
2 | Site Acquisition
3 | Concept & Planning Strategy
4 | Planning Approval
5 | Detailed Design & Building Approval
6 | Procurement
7 | Construction
8 | Commissioning & Occupancy
9 | Settlement & Handover
10 | Defects & Stabilisation

## CONSULTANTS
Primary Consultant / Responsible Party
1 | Agent
2 | Architect
3 | Asset Manager
4 | Builder
5 | Builder / Consultants
6 | Builder / Façade Engineer
7 | Builder / PM
8 | Builder / Structural Engineer
9 | Building Surveyor
10 | Civil Engineer
11 | Commissioning Manager
12 | Development Manager
13 | Development Manager / QS
14 | Environmental Consultant
15 | ESD Consultant
16 | Fire Engineer
17 | Geotechnical Engineer
18 | Landscape Architect
19 | Lawyer / Developer
20 | Licensed Surveyor
21 | Market Research Consultant
22 | MEP / ESD Consultants
23 | MEP Contractors
24 | MEP Engineers
25 | PCA / Consultants
26 | PM / QS
27 | Property Lawyer
28 | QS / PM
29 | Quantity Surveyor
30 | Strata Manager / Lawyer
31 | Structural Engineer
32 | Superintendent / PM
33 | Surveyor
34 | Town Planner
35 | Town Planner / Lawyer
36 | Traffic Engineer
37 | Various Consultants

## ACTIVITIES
StageID | Stage Name | JOB PHASE | Activity Category | Activity Description | Estimated Timeline (days) | Primary Consultant / Responsible Party | Key Deliverable / Output
1 | Strategy & Feasibility | OPPORTUNITY | Market Analysis | Undertake market and demand study | 5 | Market Research Consultant | Market demand report
1 | Strategy & Feasibility | OPPORTUNITY | Feasibility | Prepare high-level development feasibility model | 5 | Development Manager / QS | Feasibility model
1 | Strategy & Feasibility | OPPORTUNITY | Planning Due Diligence | Review zoning, overlays, planning controls | 5 | Town Planner | Planning due diligence memo
1 | Strategy & Feasibility | OPPORTUNITY | Concept Design | Prepare test fit / massing options | 25 | Architect | Concept massing drawings
1 | Strategy & Feasibility | CONTRACTED | Cost Planning | Prepare preliminary cost plan | 20 | Quantity Surveyor | Concept cost plan
1 | Strategy & Feasibility | CONTRACTED | Risk | Prepare initial development risk register | 5 | Development Manager | Risk register
2 | Site Acquisition | CONTRACTED | Legal | Review title, easements, covenants | 5 | Property Lawyer | Title due diligence report
2 | Site Acquisition | CONTRACTED | Surveying | Prepare feature & level survey | 15 | Licensed Surveyor | Feature & level survey
2 | Site Acquisition | CONTRACTED | Environmental | Undertake contamination screening (PSI) | 30 | Environmental Consultant | Contamination assessment
2 | Site Acquisition | CONTRACTED | Geotechnical | Preliminary geotechnical investigation | 30 | Geotechnical Engineer | Geotechnical advice
2 | Site Acquisition | CONTRACTED | Traffic | Assess site access feasibility | 14 | Traffic Engineer | Access feasibility advice
2 | Site Acquisition | CONTRACTED | Commercial | Negotiate land contract / option | 14 | Lawyer / Developer | Executed contract
3 | Concept & Planning Strategy | CONTRACTED | Architecture | Prepare planning concept design | 14 | Architect | Planning drawings
3 | Concept & Planning Strategy | CONTRACTED | Planning | Prepare planning strategy and pre-app advice | 14 | Town Planner | Planning strategy memo
3 | Concept & Planning Strategy | CONTRACTED | Traffic | Prepare traffic & parking concept report | 14 | Traffic Engineer | Traffic report
3 | Concept & Planning Strategy | CONTRACTED | Civil | Prepare concept stormwater & services strategy | 14 | Civil Engineer | Servicing strategy
3 | Concept & Planning Strategy | CONTRACTED | Landscape | Prepare landscape concept design | 14 | Landscape Architect | Landscape concept
3 | Concept & Planning Strategy | CONTRACTED | ESD | Prepare sustainability strategy | 14 | ESD Consultant | ESD strategy
4 | Planning Approval | CONTRACTED | Planning Application | Prepare and lodge planning permit application | 14 | Town Planner | DA submission
4 | Planning Approval | CONTRACTED | Architecture | Prepare DA architectural plans | 14 | Architect | DA drawings
4 | Planning Approval | CONTRACTED | Consultant Reports | Prepare supporting consultant reports | 14 | Various Consultants | Planning reports
4 | Planning Approval | CONTRACTED | Council Process | Respond to RFIs and objections | 14 | Town Planner | RFI responses
4 | Planning Approval | CONTRACTED | Approval | Negotiate permit conditions and obtain approval | 14 | Town Planner / Lawyer | Planning permit
5 | Detailed Design & Building Approval | CONTRACTED | Architecture | Prepare detailed design & construction documentation | 14 | Architect | IFC drawings
5 | Detailed Design & Building Approval | CONTRACTED | Structural | Prepare structural design & drawings | 14 | Structural Engineer | Structural documentation
5 | Detailed Design & Building Approval | CONTRACTED | Services | Prepare MEP design documentation | 14 | MEP Engineers | Services drawings
5 | Detailed Design & Building Approval | CONTRACTED | Fire | Prepare fire safety strategy & reports | 14 | Fire Engineer | Fire engineering report
5 | Detailed Design & Building Approval | CONTRACTED | Certification | Obtain building permit / construction certificate | 14 | Building Surveyor | Building permit
6 | Procurement | CONTRACTED | Tendering | Prepare and issue tender documentation | 14 | PM / QS | Tender package
6 | Procurement | CONTRACTED | Tender Review | Assess and level tenders | 14 | QS / PM | Tender report
6 | Procurement | CONTRACTED | Contracting | Negotiate and execute building contract | 14 | Lawyer / Developer | Executed contract
6 | Construction | CONTRACTED | Site Establishment | Mobilise site and commence works | 14 | Builder | Site establishment
6 | Construction | CONTRACTED | Structure | Construct substructure and superstructure | 14 | Builder / Structural Engineer | Completed structure
6 | Construction | CONTRACTED | Façade | Install façade systems | 14 | Builder / Façade Engineer | Façade installation
6 | Construction | CONTRACTED | Services | Install building services | 14 | MEP Contractors | Services installation
6 | Construction | CONTRACTED | Contract Admin | Administer variations, EOTs, progress claims | 14 | Superintendent / PM | Contract records
7 | Commissioning & Occupancy | CONTRACTED | Commissioning | Commission all building systems | 14 | Commissioning Manager | Commissioning records
7 | Commissioning & Occupancy | CONTRACTED | Compliance | Final inspections and compliance certifications | 14 | PCA / Consultants | Compliance certificates
7 | Commissioning & Occupancy | CONTRACTED | Handover | Prepare O&M manuals and training | 14 | Builder / Consultants | O&M manuals
7 | Commissioning & Occupancy | CONTRACTED | Occupancy | Obtain occupancy permit | 14 | Building Surveyor | Occupancy permit
8 | Settlement & Handover | CONTRACTED | Subdivision | Prepare and register plan of subdivision | 14 | Surveyor | Registered titles
8 | Settlement & Handover | CONTRACTED | Strata | Establish Owners Corporation | 14 | Strata Manager / Lawyer | OC registration
8 | Settlement & Handover | CONTRACTED | Leasing | Lease or sell completed asset | 14 | Agent | Executed leases/sales
9 | Defects & Stabilisation | CONTRACTED | Defects | Manage defects liability period | 14 | Builder / PM | Defects closed
9 | Defects & Stabilisation | CONTRACTED | Tuning | Post-occupancy building tuning | 14 | MEP / ESD Consultants | Performance reports
9 | Defects & Stabilisation | CONTRACTED | Stabilisation | Achieve target occupancy and stable operations | 14 | Asset Manager | Stabilised asset