## Activities
StageID | Stage Name | Activity Category | Activity Category | Activity Description | Estimated Timeline (days) | Primary Consultant / Responsible Party | Key Deliverable / Output | JOB PHASE
1 | Strategy & Feasibility | Market Analysis | Market Analysis | Undertake market and demand study | 5 | Market Research Consultant | Market demand report | OPPORTUNITY
1 | Strategy & Feasibility | Feasibility | Feasibility | Prepare high-level development feasibility model | 5 | Development Manager / QS | Feasibility model | OPPORTUNITY
1 | Strategy & Feasibility | Planning Due Diligence | Planning Due Diligence | Review zoning, overlays, planning controls | 5 | Town Planner | Planning due diligence memo | OPPORTUNITY
1 | Strategy & Feasibility | Concept Design | Concept Design | Prepare test fit / massing options | 25 | Architect | Concept massing drawings | OPPORTUNITY
1 | Strategy & Feasibility | Cost Planning | Cost Planning | Prepare preliminary cost plan | 20 | Quantity Surveyor | Concept cost plan | CONTRACTED
1 | Strategy & Feasibility | Risk | Risk | Prepare initial development risk register | 5 | Development Manager | Risk register | CONTRACTED
2 | Site Acquisition | Legal | Legal | Review title, easements, covenants | 5 | Property Lawyer | Title due diligence report | CONTRACTED
2 | Site Acquisition | Surveying | Surveying | Prepare feature & level survey | 15 | Licensed Surveyor | Feature & level survey | CONTRACTED
2 | Site Acquisition | Environmental | Environmental | Undertake contamination screening (PSI) | 30 | Environmental Consultant | Contamination assessment | CONTRACTED
2 | Site Acquisition | Geotechnical | Geotechnical | Preliminary geotechnical investigation | 30 | Geotechnical Engineer | Geotechnical advice | CONTRACTED
2 | Site Acquisition | Traffic | Traffic | Assess site access feasibility | 14 | Traffic Engineer | Access feasibility advice | CONTRACTED
2 | Site Acquisition | Commercial | Commercial | Negotiate land contract / option | 14 | Lawyer / Developer | Executed contract | CONTRACTED
3 | Concept & Planning Strategy | Architecture | Architecture | Prepare planning concept design | 14 | Architect | Planning drawings | CONTRACTED
3 | Concept & Planning Strategy | Planning | Planning | Prepare planning strategy and pre-app advice | 14 | Town Planner | Planning strategy memo | CONTRACTED
3 | Concept & Planning Strategy | Traffic | Traffic | Prepare traffic & parking concept report | 14 | Traffic Engineer | Traffic report | CONTRACTED
3 | Concept & Planning Strategy | Civil | Civil | Prepare concept stormwater & services strategy | 14 | Civil Engineer | Servicing strategy | CONTRACTED
3 | Concept & Planning Strategy | Landscape | Landscape | Prepare landscape concept design | 14 | Landscape Architect | Landscape concept | CONTRACTED
3 | Concept & Planning Strategy | ESD | ESD | Prepare sustainability strategy | 14 | ESD Consultant | ESD strategy | CONTRACTED
4 | Planning Approval | Planning Application | Planning Application | Prepare and lodge planning permit application | 14 | Town Planner | DA submission | CONTRACTED
4 | Planning Approval | Architecture | Architecture | Prepare DA architectural plans | 14 | Architect | DA drawings | CONTRACTED
4 | Planning Approval | Consultant Reports | Consultant Reports | Prepare supporting consultant reports | 14 | Various Consultants | Planning reports | CONTRACTED
4 | Planning Approval | Council Process | Council Process | Respond to RFIs and objections | 14 | Town Planner | RFI responses | CONTRACTED
4 | Planning Approval | Approval | Approval | Negotiate permit conditions and obtain approval | 14 | Town Planner / Lawyer | Planning permit | CONTRACTED
5 | Detailed Design & Building Approval | Architecture | Architecture | Prepare detailed design & construction documentation | 14 | Architect | IFC drawings | CONTRACTED
5 | Detailed Design & Building Approval | Structural | Structural | Prepare structural design & drawings | 14 | Structural Engineer | Structural documentation | CONTRACTED
5 | Detailed Design & Building Approval | Services | Services | Prepare MEP design documentation | 14 | MEP Engineers | Services drawings | CONTRACTED
5 | Detailed Design & Building Approval | Fire | Fire | Prepare fire safety strategy & reports | 14 | Fire Engineer | Fire engineering report | CONTRACTED
5 | Detailed Design & Building Approval | Certification | Certification | Obtain building permit / construction certificate | 14 | Building Surveyor | Building permit | CONTRACTED
6 | Procurement | Tendering | Tendering | Prepare and issue tender documentation | 14 | PM / QS | Tender package | CONTRACTED
6 | Procurement | Tender Review | Tender Review | Assess and level tenders | 14 | QS / PM | Tender report | CONTRACTED
6 | Procurement | Contracting | Contracting | Negotiate and execute building contract | 14 | Lawyer / Developer | Executed contract | CONTRACTED
6 | Construction | Site Establishment | Site Establishment | Mobilise site and commence works | 14 | Builder | Site establishment | CONTRACTED
6 | Construction | Structure | Structure | Construct substructure and superstructure | 14 | Builder / Structural Engineer | Completed structure | CONTRACTED
6 | Construction | Façade | Façade | Install façade systems | 14 | Builder / Façade Engineer | Façade installation | CONTRACTED
6 | Construction | Services | Services | Install building services | 14 | MEP Contractors | Services installation | CONTRACTED
6 | Construction | Contract Admin | Contract Admin | Administer variations, EOTs, progress claims | 14 | Superintendent / PM | Contract records | CONTRACTED
7 | Commissioning & Occupancy | Commissioning | Commissioning | Commission all building systems | 14 | Commissioning Manager | Commissioning records | CONTRACTED
7 | Commissioning & Occupancy | Compliance | Compliance | Final inspections and compliance certifications | 14 | PCA / Consultants | Compliance certificates | CONTRACTED
7 | Commissioning & Occupancy | Handover | Handover | Prepare O&M manuals and training | 14 | Builder / Consultants | O&M manuals | CONTRACTED
7 | Commissioning & Occupancy | Occupancy | Occupancy | Obtain occupancy permit | 14 | Building Surveyor | Occupancy permit | CONTRACTED
8 | Settlement & Handover | Subdivision | Subdivision | Prepare and register plan of subdivision | 14 | Surveyor | Registered titles | CONTRACTED
8 | Settlement & Handover | Strata | Strata | Establish Owners Corporation | 14 | Strata Manager / Lawyer | OC registration | CONTRACTED
8 | Settlement & Handover | Leasing | Leasing | Lease or sell completed asset | 14 | Agent | Executed leases/sales | CONTRACTED
9 | Defects & Stabilisation | Defects | Defects | Manage defects liability period | 14 | Builder / PM | Defects closed | CONTRACTED
9 | Defects & Stabilisation | Tuning | Tuning | Post-occupancy building tuning | 14 | MEP / ESD Consultants | Performance reports | CONTRACTED
9 | Defects & Stabilisation | Stabilisation | Stabilisation | Achieve target occupancy and stable operations | 14 | Asset Manager | Stabilised asset | CONTRACTED

## Reference - Stages
Stage Number | Stage Name
1 | Strategy & Feasibility
2 | Site Acquisition
3 | Concept & Planning Strategy
4 | Planning Approval
5 | Detailed Design & Building Approval
6 | Procurement
7 | Construction
8 | Commissioning & Occupancy
9 | Settlement & Handover
10 | Defects & Stabilisation

## Reference - Consultants
# | Consultant Name
1 | Agent
2 | Architect
3 | Asset Manager
4 | Builder
5 | Builder / Consultants
6 | Builder / Façade Engineer
7 | Builder / PM
8 | Builder / Structural Engineer
9 | Building Surveyor
10 | Civil Engineer
11 | Commissioning Manager
12 | Development Manager
13 | Development Manager / QS
14 | Environmental Consultant
15 | ESD Consultant
16 | Fire Engineer
17 | Geotechnical Engineer
18 | Landscape Architect
19 | Lawyer / Developer
20 | Licensed Surveyor
21 | Market Research Consultant
22 | MEP / ESD Consultants
23 | MEP Contractors
24 | MEP Engineers
25 | PCA / Consultants
26 | PM / QS
27 | Property Lawyer
28 | QS / PM
29 | Quantity Surveyor
30 | Strata Manager / Lawyer
31 | Structural Engineer
32 | Superintendent / PM
33 | Surveyor
34 | Town Planner
35 | Town Planner / Lawyer
36 | Traffic Engineer
37 | Various Consultants

## Reference - Phases
Phase Value
OPPORTUNITY
QUOTING
WON_AWAITING_CONTRACT
CONTRACTED
LOST